## Bug report
ABZ insurance defect report- Cycle 1 Testing
| Prepared By | K.E Satwik Goud
Defect ID | Defect Description | Steps to reproduce | Severity | Status | Created by | Assigned to | Screenshot
1 | The "Save" button within the Claim Details screen appears clickable but does not save the entered claim data. Clicking the "Save" button results in an error message indicating that the claim failed to be added. | 1.Launch the application. 2.Log in with valid credentials. 3.Navigate to the "Claims" section. 4.Click on the "Get Claim" button. 5.Enter a valid claim number (e.g., "CLA1234564"). 6.Enter all the required claim details (Claim Date, Policy Number, Incident Date, etc.). 7.Click on the "Save" button. Expected Result: The "Save" button should be clickable and responsive. Upon clicking "Save," the entered claim data should be successfully saved to the system. The application should display a success message or navigate to a confirmation screen. Actual Result: The "Save" button appears clickable but does not save the entered claim data. An error message is displayed (e.g., "Failed to add claim," "Error saving claim") indicating that the save operation was unsuccessful. | 1-High | Open | K.E Satwik Goud | Adi Lakshmi | https://ibb.co/SrK89rk
2 | The "Get" button within the Claim Details screen appears clickable, but clicking it does not retrieve and display the corresponding claim information. No data is populated in the fields below the button (Claim Date, Policy No., etc.) even after clicking "Get." | 1.Launch the application. 2.Log in with valid credentials. 3.Navigate to the "Claims" section. 4.Click on the "Get Claim" button. 5.Enter a valid claim number (e.g., "CLA1234564") in the provided field. 6.Click the "Get" button. Expected Result: The application should retrieve the claim information associated with the entered claim number from the backend. The retrieved data should be displayed in the corresponding fields on the screen (Claim Date, Policy No., Incident Date, etc.). Actual Result: After clicking the "Get" button, the fields remain empty. No claim information is displayed. | 1- High | Open | K.E Satwik Goud | Adi Lakshmi | https://ibb.co/NxxgWT4
3 | The application crashes when the user clicks on the "Add-ons" section within the product details page. | 1.Launch the application. 2.Navigate to a product page (e.g., by searching or browsing). 3.Tap on the product to view its details. 4.Locate the "Add-ons" section (if present) and tap on it. Expected Result: The application should smoothly display the available add-ons for the selected product, allowing the user to explore and select desired options. Actual Result: The application crashes unexpectedly. The app may freeze, become unresponsive, or force close. An error message may or may not be displayed. | 1-High | Open | K.E Satwik Goud | Adi Lakshmi | https://ibb.co/JtCNRSb